## Risk Register
CloudSync Technologies - Information Security Risk Register
Risk ID | Risk Description | Asset/Process | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Treatment Plan | Owner
R-001 | Unauthorized access to customer data due to weak authentication | Customer Database | Malicious Actor | No MFA on admin accounts | 4 | 5 | 20 | Critical | Implement MFA for all privileged accounts within 60 days | IT Security Lead
R-002 | Data breach from unpatched vulnerabilities | Production Servers | Cyber Attackers | Delayed patching process | 4 | 5 | 20 | Critical | Establish 30-day patch SLA and automated scanning | Security Manager
R-003 | Ransomware attack impacting business operations | All Systems | Ransomware Groups | Insufficient backup testing | 3 | 5 | 15 | High | Implement immutable backups and quarterly DR tests | IT Manager
R-004 | Insider threat - data exfiltration by employee | Sensitive Data | Malicious Insider | No DLP solution | 2 | 4 | 8 | Medium | Deploy DLP solution and user activity monitoring | CISO
R-005 | Cloud misconfiguration exposing data publicly | AWS S3 Buckets | Misconfiguration | Lack of configuration standards | 3 | 4 | 12 | High | Implement cloud security posture management tool | Cloud Architect
R-006 | Phishing attack compromising user credentials | Email System | Phishing Attackers | Limited security awareness | 4 | 3 | 12 | High | Conduct quarterly phishing simulations and training | Security Manager
R-007 | Third-party vendor data breach | Vendor Systems | Supply Chain Attack | No vendor security assessments | 3 | 4 | 12 | High | Implement third-party risk management program | Compliance Manager
R-008 | Loss of data due to inadequate backup procedures | Critical Data | Hardware Failure | Untested backup restoration | 2 | 4 | 8 | Medium | Document and test backup/restore procedures monthly | IT Operations
R-009 | Compliance violation due to lack of audit trail | Audit Logs | Regulatory Audit | Insufficient logging | 3 | 3 | 9 | Medium | Implement centralized logging with 1-year retention | Compliance Manager
R-010 | API security vulnerabilities exposing data | API Gateway | API Exploitation | Weak API authentication | 3 | 4 | 12 | High | Implement API gateway with rate limiting and OAuth 2.0 | Dev Manager
R-011 | Physical security breach at office location | Office Premises | Unauthorized Entry | No monitoring system | 2 | 3 | 6 | Medium | Install surveillance cameras and access logs | Facilities Manager
R-012 | Mobile device loss containing sensitive data | Corporate Devices | Device Theft/Loss | No remote wipe capability | 3 | 3 | 9 | Medium | Deploy MDM solution with encryption and remote wipe | IT Manager
Risk Summary
Total Risks: | 12 | Critical Risks: | 2
Average Risk Score: | 11.9167 | High Risks: | 5
Risks Requiring Immediate Action: | 7 | Medium Risks: | 5
Risk Scoring Methodology:
Likelihood Scale: 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain
Impact Scale: 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Catastrophic
Risk Score = Likelihood × Impact
Risk Levels: Critical (≥15), High (10-14), Medium (5-9), Low (<5)